We wrześniu  2018 r. Zespół Szkół Nr 1 w Tychach uzyskał fundusze na realizację nowego projektu unijnego w ramach akcji 2 – Partnerska Współpraca Szkół w programie Erasmus+

pt. ,,KEEP CALM AND BE GREEN .''nr 2018-1-PL01-KA229-050583_1 zostając jednocześnie koordynatorem projektu.

Projekt jest kombinacją działań w latach 2018-2020 z zakresu geografii , fizyki , matematyki , biologii i obejmuje poznawanie przez uczniów (pod kierunkiem nauczycieli) odnawialnych źródeł energii i ich wykorzystania w swoich krajach . W czasie wizyt roboczych w poszczególnych krajach uczniowie prezentują swoje prace i dzielą się swoją wiedzą z pozostałymi uczestnikami projektu. Językiem roboczym projektu jest język angielski. Kraje partnerskie to  Grecja , Włochy Macedonia , Finlandia , Portugalia , a koordynatorem jest Polska.

Działania :

| Data | Miejsce , dni |
| --- | --- |
| Styczeń 2019 | Polska Let’s meet each other |
| Kwiecień 2019 | FYROM 5 Sun Power |
| Wrzesień 2019 | Sycylia Water Power |
| Luty 2020 | Finlandia Wind Power |
| Kwiecień 2020 | Chios Geothermal Power |

Koordynatorem projektu jest Pani Beata Sobel

W dniach 13.01- 19.01.2019 będziemy gościć szkoły partnerskie w Tychach.

Kalendarz działań na lata 2019-2020

KEEP CALM AND BE GREEN : CALENDAR OF ACTIVITIES

First Year 2018/2019

| Date | Activity | Description | Results | Responsible |
| --- | --- | --- | --- | --- |
| September 2018 | Erasmus+ Corner in partner schools | Partners prepare display of basic info about the Project , Partners , Activities | Exhibition | All partners |
| January 2019 | first project meeting (teachers only) ‘’Let’s know each other”. | 1.Organizing the project work. Rescheduling the callendar 2.Preparing Monitoring and Evaluation activity planning table. 3.Creating joint website . 4.Contest for logo of the project. 5.Cultural visit to historical city of Kraków 6.Visiting Auschwitz Birkenau IIWW Museun 7.Students' facility excursions : -Pumped-storage hydroelectricity Żar , -visit Queen Luiza Adit Museum in Zabrze(as an example of traditional energy source) 8.Workshops on the use of ICT for the purpose of the project 9. Erasmus + News ( project magazine) No 1 | Detailed callendar , Monitoring and Evaluation Plan and evaluation documents Website (etwinning) Project’s logo Reports Reports Reports Reports PPP presentation Magazine | Poland All partners All partners All partners All partners All partners All partners All partners All partners Poland (ICT teacher) Poland (English teacher , Polish teacher |
| February 2019 | first meeting evaluation. | Filling Surveys | Surveys, Report | All partners |
| March 2019 | Dictionary of RES (in 7 languages) | Countries prepare translation of English terms into their languages. | Mini dictionary | Portugal (prepares electronic version) |
| April 2019 | second project meeting Meeting in FYROM THE SUN POWER | 1.Workshops in Nikola Karyev School.Students will present their findings about solar energy in their countries 2.An excursion to the Wind Farm Bogdanci 3.A visit to Ministry of Environment 4.Workshop with ECO N.G.O 5.A trip to MATKA 6. Activities at school according to the curriculum of the subjects concerned (cross curricular approach: physics, geography, biology, foreign languages) 7. Erasmus + News ( project magazine) No2 | PPP Report Seminar Report Report Magazine | FYROM All partners All partners All partners FYROM All partners FYROM FYROM (English teacher |
| May 2019 | Second meeting evaluation. | Filling Surveys | Surveys, Report | All partners |
| June 2019 | First project year evaluation | Filling Surveys | Surveys, Report | All partners Poland coordinator (prepares First Year Report) |

Second Year 2019/2020

| Date | Activity | Description | Results | Responsible |
| --- | --- | --- | --- | --- |
| October 2019 | Third project meeting Meeting in Sicilly WATER POWER | 1.Workshop about exploitation of rivers 2.Visit to pump storage plant 3.Visit to Catania University ‘’Water and photovoltaic technology” 4.Institutional approach (visits to institutions) 5.Visit to Catania and areas 6.Social events 7.Erasmus + News ( project magazine) No3 | PPP Reports Seminar Reports Reports Reports Magazine | Sicilly All partners All partners Sicilly All partners Sicilly All partners All partners All partners Sicilly (English teacher |
| November 2019 | Third meeting evaluation | Filling Surveys | Surveys, Report | All partners |
| January 2020 | Fourth project meeting Meeting in Finland WIND POWER | 1. Workshops about wind Energy 2.Field trips to Kalajoki , Maaninka Korkeakoski , Kasurila 3.Painting mural 4.Lessons about RES 5. .Erasmus + News ( project magazine) No4 | PPP , short dramas Reports Mural Educational resources Magazine | Finland All partners All partners Finland All partners All partners Finland (English teacher |
| February 2020 | Fourth meeting evaluation | Filling Surveys | Surveys, Report | All partners |
| April 2020 | Fifth project meeting Meeting in Chios HEAT ENERGY.ARE WE GREEN? | 1.Workshop about geothermal Energy (students findings) 2.Presenting model of Green City 3.Field trips ( solar panels , wind generators) 4.Cultural visits to Kampos , Chios castle 5.Writting the Final Report 6.Final assesment of the project and final evaluation 7.Erasmus + News ( project magazine) No5 | PPP Model Reports Reports Final Report Final Report Magazine | Chios All partners Chios All partners All partners All partners All partners Chios (English teacher) |